## Summary
PROJECT NAME | TomYang University Admission System
Module Name | Admission Criteria Management
Testing Type: | [testing technique used e.g. Functional & Regression Testing]
Prepared By: | Oliver D. Inton II
Date: | 2025-04-28
Test Environment
Environment: | QA Server
Browser/OS: | Chrome v122, Windows 11
Test Execution Summary
Total Test Cases | Passed | Failed | Blocked | Not Run
18 | 8 | 2 | 0 | 8
Defects Summary
Total Bug Count | Critical | High | Medium | Low | Trivial
2 | 1 | 0 | 1 | 0 | 0
Highlights
All critical test cases passed.
One blocker defect found during early testing, resolved before regression.
Testing completed 2 days ahead of schedule.
Risks & Issues
Risk: New code was not unit-tested by the dev team.
Issue: Blocked test case due to API timeout; dev team investigating.
Recommendations
Proceed with UAT phase after resolving open issues.
Include unit testing in the next release cycle.

## Account Management
# | TEST SCENARIO / FUNCTION | # | TEST CASE DESCRIPTION | PRE-CONDITION | TEST STEPS | TEST DATA | EXPECTED RESULT | POST CONDITION | ACTUAL RESULT | PASS/FAIL | STEPS TO REPLICATE / REMARKS
1.1 | Select College | 1 | Applicant should be able to choose desired college on the list. | User must be at the home page. | 1) Click Select College 2) Choose Desired College | College of Education | Display the chosen college. | N/A | Display the chosen college. | PASSED
1.2 | Program Code | 2 | Applicant should be able to choose desired program on the list. | User must be at the home page. | 1) Click Select Program 2) Choose Desired Program Code | BSEd EN | Display the program code, program type, description, and total units. | N/A | Display the program code, program type, description, and total units. | PASSED
1.3 | Clear | 3 | Applicant should be able to clear all the data input. | User must be at the home page. | 1) Click Clear | N/A | The data input should be cleared after clicking the clear button. | The data input should be cleared after clicking the clear button. | The data input is not cleared after clicking the clear button. | FAILED | Fix the code whereas the code when input is clicked will put blank on the data fields.
1.4 | Next | 4 | Applicant should be put into the next tab, student form to fill it up. | User must finish first the college and program selection at home page. | 1) Fill up first the Select College 2) Fill up the desired program 3) Click Next | N/A | Applicant should be put into the next tab, student form to fill it up. | N/A | Applicant is put into the next tab student form. | PASSED
2.1 | Personal Information | 5 | Applicant should be able to input data into the text fields full name, date of birth, email, mobile number, year level, select program, and date applied. | User must be at fill up page and should be finished at choosing college and program code. | 1) Click Text Fields | "Full Name: Jane Doe Age: 45 Email: janedoe@gmail.com Mobile Number: 09123456789 Year Level: 2nd Year Program: COED - BSEd EN (Undergraduate) Date Applied: 01/01/2025" | Applicant should be able to see the information they input in the text fields. | N/A | Information is input and is ready to submitted if the following requirements are done. | PASSED
2.2 | Admission Workflow | 6 | Applicant should be able to check the checkbox if they are done in the requirements. | User must be at fill up page and should be finished at choosing college and program code. | 1) Click Checkbox | Step 1: Application Submitted (Click the checkbox) | Applicant should be able to see the check in checkboxes. | N/A | Information is input and is ready to submitted if the following requirements are done. | PASSED
2.3 | Document Requirements | 7 | Applicant should be able to put document name, document type, and its description. | User must be at fill up page and should be finished at choosing college and program code. | 1) Click Text Fields | "Document Name: Form 137 Document Type: PDF Description: PDF file of my Form 137" | Applicant should be able to see the information they input in the text fields. | N/A | Information is input and is ready to submitted if the following requirements are done. | PASSED
2.4 | Interview | 8 | Applicant should be able to put number of interviewer and passing percentage. | User must be at fill up page and should be finished at choosing college and program code. | 1) Click Text Fields | "No. of Interviewer: 2 Passing Percentage (%): 80%" | Applicant should be able to see the information they input in the text fields. | N/A | Information is input and is ready to submitted if the following requirements are done. | PASSED
2.5 | Admission Test | 9 | Applicant should be able to input passing score and max score for admission test. | User must be at fill up page and should be finished at choosing college and program code. | 1) Click Text Fields | "Passing Score: 50 Max Score: 100" | Applicant should be able to see the information they input in the text fields. | N/A | Information is input and is ready to submitted if the following requirements are done. | PASSED
2.6 | Submit | 10 | Applicant should be able to click the submit button to submit all the data that they input. | User must be at fill up page and should be finished filling up all that is required. | 1) Click Submit button | N/A | Applicant should be able to see that they have successfully submitted the fill up form. | N/A | The next page is not working after clicking submit. | FAILED
3.1 | Application Dashboard Tab | 11 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.2 | Admission Criteria Tab | 12 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.3 | Application Form Tab | 13 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.4 | Document Requirements Tab | 14 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.5 | Interview Schedule Tab | 15 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.6 | Admission Test Tab | 16 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.7 | Admission Result Tab | 17 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN
3.8 | FAQs Tab | 18 | Applicant should be able to click the Application Dashboard Tab to be move to the desired tab. | User must hover at the dashboard at the left side and must click the desired button. | 1) Hover the mouse into the dashboard 2) Click the Desired Tab | N/A | Applicant must be move to the desired tab. | N/A | The applicant is not moved to the tab and is still on the current tab. The dashboard buttons for tabs is not working. | NOT RUN

## BugReport
BUG-ID | TITLE | SEVERITY | FIX STATUS
BUG-1012 | Error when clicking clear button | MEDIUM | ONGOING FIX
BUG-1013 | Error when submitting fill up form | CRITICAL | ONGOING FIX

## source
Test Result
PASSED | actual result meets expected result
FAILED | actual result does not meet expected result
BLOCKED | test case can't be executed due to a blocker e.g. API connection is down
NOT RUN | test case not executed
Severity refers to how serious the bug is from a technical/system impact perspective — how badly it affects the software’s functionality or performance.
CRITICAL | Showstopper: Complete failure or crash of the system. No workaround available. Action: Needs immediate fix before any release.
HIGH | Major: Major functionality is broken; application works but a key feature fails.Action: Needs to be fixed before release, but system remains partially usable.
MEDIUM | Moderate: A non-critical function doesn't work properly; workaround available. Action: Fix needed, but not urgent. Can wait until the next build.
LOW | Minor: Cosmetic or UI issues that do not affect functionality. Action: Can be fixed in later cycles or post-release.
TRIVIAL | Enhancement/Informational: Not actually a bug, but a suggestion or minor improvement. Action: Often logged for future consideration.
OPEN | new bug issue
PENDING | fix to be done is already assessed but actual fixing is still pending; low/medium severity
ONGOING FIX | fix is ongoing
FIXED | fixed is already done
N/A | for trivial severity